## Worksheet
Employee Management Project Timeline (Summary View)
Project Phase | Key Activities | Responsible Team | Start Date | End Date | Status
Planning & Initiation | Define project scope and objectives | Project Management Office (PMO) | 2024-01-05 | 2024-01-15 | In Progress
| Identify key stakeholders and roles | HR Department & PMO | 2024-01-08 | 2024-01-18 | In Progress
| Develop project charter and approval process | PMO Lead, HR Director | 2024-01-10 | 2024-01-25 | Pending Approval
Design & Development | Design employee onboarding workflow | HR Team, UX Designers | 2024-01-28 | 2024-02-15 | Pending Start
| Develop HR management system features (user profiles, leave tracking) | IT Development Team | 2024-02-01 | 2024-03-31 | Pending Start
| Create training modules for new system rollout | Training & Development Team | 2024-02-15 | 2024-03-15 | Pending Start
Implementation & Testing | Conduct user acceptance testing (UAT) | QA Team, HR Champions | 2024-04-01 | 2024-04-30 | Pending Start
| Deploy system to production environment | IT Operations Team, PMO | 2024-05-01 | 2024-05-15 | Pending Start
| Roll out to all employees with support team on standby | HR, IT Support, PMO | 2024-05-16 | 2024-05-31 | Pending Start
Post-Launch & Review | Monitor system performance and user feedback | Support Team, PMO | 2024-06-01 | 2024-06-30 | Pending Start
| Conduct project retrospective and finalize documentation | PMO, HR Leadership | 2024-07-01 | 2024-07-15 | Pending Start
Project Total Duration: |  |  | 2024-01-05 to 2024-07-15 (6 months)