## Worksheet
Phase | Task Name | Responsible Employee(s) | Start Date | End Date | Status | Description
Initiation | Project Kick-off Meeting | John Smith, Jane Doe | 2024-01-15 | 2024-01-17 | In Progress | Align team goals and define project scope.
Planning | Resource Allocation & Scheduling | Alice Johnson, Bob Wilson | 2024-01-18 | 2024-01-31 | To Do | Distribute roles and set timeline milestones.
Execution | Onboarding New Team Members | Sarah Brown, Mike Davis | 2024-02-01 | 2024-02-15 | To Do | Complete training and integration of new hires.
Execution | Performance Evaluation Setup | Lisa Taylor, James Moore | 2024-02-16 | 2024-03-15 | To Do | Create evaluation criteria and tools.
Closure | Project Review & Feedback Session | All Team Members, HR Lead | 2024-03-16 | 2024-03-25 | To Do | Evaluate outcomes and collect team feedback.