## Worksheet
Employee Management - Project Tracker
Project Overview (Page 1)
Project ID | Project Name | Manager | Status | Budget (USD) | Start Date | End Date
P001 | Website Redesign Initiative | Jane Smith | In Progress | 50,000 | 2024-11-01 | 2025-03-31
P002 | CRM Integration Project | John Doe | Planning | 75,000 | 2024-12-15 | 2025-06-30
P003 | Mobile App Development | Alice Johnson | On Hold | 120,000 | 2024-11-15 | 2025-12-31
Project Progress Summary (Page 1)
Project ID | % Complete | Tasks Completed | Upcoming Milestones
P001 | 65% | 23/35 | UI Testing - Dec 10, 2024
P002 | 15% | 3/20 | Requirements Finalized - Jan 5, 2025
P003 | 8% | 1/12 | Architecture Approval - Dec 1, 2024
Employee Assignments (Page 1)
Employee Name | Role | Project ID | Hours/Week | Status (Active)
Robert Brown | Frontend Developer | P001 | 35 | Yes
Sarah Wilson | CMS Specialist | P001 |  | 25 |  | Yes
Michael Lee | Data Analyst | P002 | 15 | No (Part-time)
KPI Dashboard (Page 1)
KPI Metric | Target | Current Value | Status
Project On-Time Completion Rate | 90% | 84% | Warning
tr >< tr > tr >
Resource Allocation (Page 2)
Employee Name | Department | Total Hours Allocated | Utilization Rate (%) | Avg. Weekly Load (Hours)
Robert Brown | IT Development | 120
tr >
Timeline Gantt Chart Summary (Page 2)
Project ID | Task | Start Date
P001 | Design Phase
tr >
Departmental Workload (Page 2)
Department
tr >
Meeting Schedule (Page 2)
Date | Time
tr >
Employee Performance & Development (Page 3)
Employee Name | Position
tr >
Training & Skill Development (Page 3)
Employee
tr >
Leave & Attendance Summary (Page 3)
Employee Name
tr >
Project Risks & Issues (Page 4)
Risk ID
tr >
Change Requests (Page 4)
Request ID
tr >
Project Documentation (Page 4)
Document Type