## Annual Budget - Tracking View
ANNUAL EVENT PLANNING BUDGET - TRACKING VIEW
Category | Budgeted Amount ($) | Actual Spend ($) | Remaining Budget ($) | Status | Notes
Event Planning & Logistics
Venue Rental | 10,000.00 | 9,500.00 | 500.01 | On Track | Minor adjustments due to early booking discount.
Marketing & Promotion | 5,000.00 | 3,875.25 | 1,124.75 | On Track | Pre-event campaign in progress.
Event Staffing & Services | 8,000.00 | 7,234.50 | 765.51 | On Track | Hired through preferred vendor.
Entertainment & Activities
Performing Arts Group | 6,000.00 | 5,874.32 | 125.68 | On Track | Contract signed and payment made.
Interactive Workshops | 3,500.00 | 2,987.65 | 512.34 | On Track | One session postponed.
Catering & Hospitality
Food & Beverages | 15,000.00 | 14,238.91 | 761.09 | On Track | Menu finalized and tested.
Desserts & Refreshments | 2,500.00 | 1,943.78 | 556.22 | On Track | Additional guests expected.
Miscellaneous & Contingency
Decorations & Signage | 4,000.00 | 3,789.21 | 210.79 | On Track | Custom designs in production.
Contingency Fund | 5,000.00 | 1,234.56 | 3,765.44 | On Track | Reserved for unexpected costs.
Total Budget Summary | 59,000.00 | 52,778.18 | 6,221.82 | On Track | Budget under control with healthy contingency.