## Worksheet
Event Planning Business Plan - Client View
Category | Item Description | Target Date | Status | Budget (USD) | Actual Cost (USD) | Notes
Event Overview | Event Title & Theme | 2024-03-15 | In Progress | 1,500.00 |  | Annual Gala - "Stars of the Future"
| Event Type | 2024-03-16 | In Progress | 500 |  | Celebration & Networking Event
| Target Audience Size | 2024-03-17 | In Progress | 1,000.00 |  | Approximately 350 guests
| Event Date & Time | 2024-03-18 | In Progress | 750 |  | Saturday, June 15, 2024 ¦ 6:30 PM – 11:30 PM
| Venue Location | 2024-03-19 | In Progress | 5,500.00 |  | The Grand Ballroom, Downtown Convention Center
Planning & Logistics | Sub-Item | Target Date | Status | Budget (USD) | Actual Cost (USD) | Notes
Venue & Facilities
| Venue Booking & Contract Signing | 2024-04-15 | Completed | 3,000.00 | 3,150.56 | Signed agreement with venue provider.
| A/V Equipment Rental (Stage, Lights, Sound) | 2024-04-25 | In Progress | 1,800.00 |  | Budget includes setup and technician support.
Catering & Refreshments
| Menu Design & Tasting Session | 2024-05-10 | In Progress | 1,200.00 |  | Catering partner: Elegant Bites Inc.
Guest Management
Invitation Design & Distribution | 2024-05-01 | In Progress | 600 |  | Digital invites via Eventbrite + email blast.
Marketing & Promotion
Official Launch Campaign (Social Media, Email) | 2024-05-15 | In Progress | 3,000.00 |  | Focused on targeted outreach via LinkedIn and Instagram.
Staffing & Services
Hire Event Coordinator & Assistant Team | 2024-04-30 | In Progress | 5,000.00 |  | Team of 8 professionals including logistics and guest services.
Vendor Management
Contract Finalization with All Vendors | 2024-05-31 | Pending | 6,500.00 |  | Includes photography, floral design, security.
Post-Event
Feedback Collection & Survey Distribution | 2024-06-18 | Pending | 450 |  | Send survey to all attendees via email.
Total Projected Budget |  |  |  | $25,300.00 | $3,150.56 (Actual to Date) | Based on initial plan; ongoing cost tracking.