## Worksheet
Event Planning Business Plan - Manager View
Project Phase | Key Activities | Responsible Team | Status | Start Date | End Date | Budget (USD)
Planning Phase | Define event objectives and scope | Strategy Team | In Progress | 2024-01-05 | 2024-01-15 | $7,500
| Identify target audience and stakeholders | Marketing & Research Team | Not Started | 2024-01-07 | 2024-01-18 | $3,200
| Develop initial event concept and theme | Design & Creative Team | In Progress | 2024-01-10 | 2024-01-25 | $5,800
| Outline timeline and milestones (Gantt) | Project Management Office | In Progress | 2024-01-12 | 2024-01-30 | $3,500
Procurement Phase | Solicit vendor proposals (venue, catering) | Procurement Team | Not Started | 2024-01-28 | 2024-02-15 | $65,000
| Promotion & Marketing Phase | Launch digital marketing campaign (social media, email) | Marketing Team | Not Started | 2024-02-01 | 2024-03-15 | $38,500
|  | Logistics & Operations Phase | Finalize venue setup and layout plan | Operations Team | Not Started | 2024-03-01 | 2024-03-25 | $18,900
Coordinate transportation and accommodations for guests |  |  | Logistics Team | Not Started | 2024-03-10 | 2024-04-15 | $14,600
Execution Phase | Event day coordination and on-site management |  | Event Operations Team | Not Started | 2024-04-18 | 2024-04-18 | $55,750
| Evaluation & Reporting Phase |  | Post-event survey distribution and analysis | Research & Insights Team | Not Started | 2024-04-19 | 2024-05-15 | $8,300
|  | Compile performance report and ROI summary | Finance & Analytics Team | Not Started | 2024-05-10 | 2024-05-31 | $6,800
Wrap-up & Handover Phase |  | Finalize vendor payments and contracts closure | Finance Team | Not Started | 2024-05-16 | 2024-06-15 | $7,900
| TOTAL PROJECT BUDGET: | [5 empty] | $245,350
Notes:All dates are approximate. Status indicators: Not Started, In Progress, Complete.
This table is designed for managerial oversight and business planning purposes. Update progress regularly to maintain accuracy.