## Worksheet
Phase | Task/Activity | Responsible Party | Deadline | Status | Budget Allocation ($)
Planning & Research | Define event objectives and target audience | Event Manager | 2023-10-15 | Pending | 500
| Conduct market research and competitor analysis | Marketing Coordinator | 2023-10-25 | In Progress | 750
| Select event date and venue | Facility Coordinator | 2023-11-05 | Pending | 1,200.00
Marketing & Promotion
Pre-Event Marketing | Develop branding and visual identity | Graphic Designer | 2023-10-20 | In Progress | 800
| Create promotional materials (digital & print) | Marketing Team | 2023-11-15 | Pending | 1,500.00
| Launch social media campaign | Social Media Manager | 2023-11-10 | Pending | 600
Logistics & Operations
Vendor Coordination | Hire catering and food service providers | Procurement Officer | 2023-11-08 | Pending | 4,500.00
| Arrange audiovisual and technical support | Technical Coordinator | 2023-11-12 | Pending | 3,000.00
| Secure event insurance and permits | Legal & Compliance Officer | 2023-11-15 | Pending | 900
On-Site Execution
Event Day | Set up venue and equipment | Operations Team | 2023-12-10 (8:00 AM) | Pending | 1,800.00
| Coordinate speaker and guest management | Guest Relations Officer | 2023-12-10 (9:30 AM) | Pending | 600
Total Budget: |  |  |  |  | 16,150.00
Note:This is a planning view template for business event planning. Adjust dates, responsibilities, and budget as needed.