## Worksheet
Event Planning - Business Plan Summary View
Category | Description | Target Date | Status
Event Overview | Annual Corporate Summit featuring keynote speakers, networking sessions, and product launches. | 2024-11-15 | In Progress
Event Objectives | Increase brand visibility by 30%, generate 200+ qualified leads, and improve stakeholder engagement. | 2024-11-15 | Completed
Budget Overview | Total Budget: $85,000 ¦ Allocated: $78,350 ¦ Remaining: $6,650 | 2024-11-15 | In Progress
Location & Venue | Grand Horizon Convention Center, 800 attendees capacity, AV and catering included. | 2024-10-25 | Confirmed
Schedule & Timeline | Daily agenda: Opening Ceremony, Keynote Sessions, Breakout Workshops, Closing Gala. | 2024-11-15 | Approved
Marketing & Promotion | Email campaigns, social media outreach, partner co-marketing, and influencer collaboration. | 2024-11-01 | In Progress
Speaker & Presenter Management | Confirmed 5 keynote speakers; 3 workshop leaders scheduled. | 2024-10-30 | Completed
Attendee Registration | Online portal live; registration target: 750 attendees. | 2024-11-10 | In Progress
Logistics & Operations | Transportation, accommodations, signage, security, and on-site staff coordination. | 2024-11-05 | In Progress
Post-Event Evaluation | Survey distribution, ROI analysis, and stakeholder feedback collection. | 2024-11-30 | Pending
Total |  |  | 8/10 Tasks Completed