## Worksheet
Weekly Business Plan - Event Planning
Week Starting | Event Name | Location | Planned Budget ($) | Status | Key Activities | Action Items / Follow-ups (Due Date)
Mon, Apr 1, 2024 | Q2 Launch Event | New York Convention Center | 35,000 | Pending Approval | Creative brief finalization Digital campaign kickoff Venue contract review | Finalize event theme - Apr 4, 2024 | Submit vendor quotes - Apr 5, 2024
Mon, Apr 8, 2024 | Team Building Retreat | Catskill Mountain Lodge | 15,000 | In Progress | Confirm attendance Select team activities Book transportation & accommodations | Schedule team workshop - Apr 10, 2024 | Send RSVPs - Apr 12, 2024
Mon, Apr 15, 2024 | Product Showcase Expo | Silicon Valley Tech Park | 50,000 | Budget Approved | Floor plan design Booth setup planning Sponsorship outreach initiated | Finalize exhibitor list - Apr 18, 2024 | Confirm keynote speaker - Apr 19, 2024
Mon, Apr 22, 2024 | Celebration Gala Night | Luxury Downtown Ballroom | 85,000 | Planning Phase | Menu tasting Celebrity guest coordination Luxury vendor negotiations | Negotiate lighting package - Apr 24, 2024 | Send save-the-dates - Apr 25, 2024
Mon, Apr 29, 2024 | Fundraising Charity Drive | Community Center Plaza | 18,000 | Pending Approval | Digital donation platform setup Volunteer recruitment Sponsorship outreach launched | Create promotional video - May 2, 2024 | Approve event permit - May 3, 2024
Total Budget This Week: |  |  | $203,000 |  |  | Next Action Deadline: May 3, 2024