## Worksheet
Event Planning Master Template
Phase | Task Description | Responsible Party | Deadline | Status
Phase 1: Initial Planning | Define event objectives, budget, and target audience.
1.1 | Define event purpose and goals | Event Manager | 2023-10-05 | In Progress
Phase 2: Logistics & Venue Selection
2.1 | Identify and book suitable venue(s) | Venue Coordinator | 2023-10-15 | Pending
Phase 3: Vendor Management & Contracts
3.1 | Finalize catering vendor contract | Catering Manager | 2023-10-20 | Pending
Phase 4: Marketing & Communication Strategy
4.1 | Design event invitation and email campaign | Marketing Specialist | 2023-10-25 | Pending
Phase 5: Final Preparations & Run of Show
5.1 | Create detailed run-of-show schedule | Event Coordinator | 2023-11-05 | Pending
© 2023 Event Planning Solutions ¦ Multi-Page Business Template ¦ Page 1 of 4
Event Budget Overview (Page 2)
Budget Category | Estimated Cost ($) | Actual Cost ($) | Variance ($)
Venue Rental | 15,000.00
Catering (Per Guest) | 75
Audio & Visual Equipment
Projectors & Screens | 2,500.00
Staffing & Personnel
Event Staff (12 people) | 7,200.00
Marketing & Promotion
Printed Invitations | 1,200.00
Contingency (15%)
Total Estimated Budget | 32,500.00
© 2023 Event Planning Solutions ¦ Multi-Page Business Template ¦ Page 2 of 4
Attendee List & RSVP Tracker (Page 3)
Full Name | Email Address | Company | Status (RSVP) | Dietary Restrictions
John Smith | john.smith@company.com | ABC Corp. | Confirmed | Vegan, No Nuts
Sarah Johnson | sarah.j@innovate.com | Innovate Solutions | Confirmed | Gluten-Free Only
Michael Brown | michael.b@techflow.com | TechFlow Inc. | Pending | None
Lisa Davis | davis.l@globalreach.com | Global Reach Group | Declined | Vegetarian
Raj Patel | raj.p@futuretech.com | FutureTech Systems | Confirmed | No Dairy, Halal Preferred
Summary:
Total Invited: 25
Confirmed Attendees: 18
Pending Responses: 3
Declined: 4© 2023 Event Planning Solutions ¦ Multi-Page Business Template ¦ Page 3 of 4
Event Day Timeline & Responsibilities (Page 4)
Time | Activity | Responsible Team | Status Check
07:00 AM – 10:30 AM | Setup & Preparation Phase
07:00 AM | Venue arrival and security check-in | Safety & Security Team | Pending
10:30 AM – 12:00 PM | Final Venue Setup & Tech Checks
10:45 AM | Audio/Visual system testing with vendors | AV Team Lead | Pending
12:00 PM – 1:30 PM | Catering Service & Guest Welcome
12:05 PM | Catering team begins food service setup | Catering Manager | Pending
1:30 PM – 3:00 PM | Main Speaker Session #1
1:35 PM | Host introduces keynote speaker | Emcee Team | Pending
3:00 PM – 3:30 PM | Coffee Break & Networking
3:15 PM | Serve refreshments and monitor attendee flow | Catering & Volunteer Team | Pending
4:00 PM – 5:30 PM | Closing Remarks & Feedback Collection
4:55 PM | Distribute feedback forms to attendees | Event Coordinator | Pending
Post-Event Instructions:
- All equipment must be returned by 6 PM
- Debrief meeting scheduled for October 25 at 10 AM