## Worksheet
Event Planning - Chore Chart (Client View)
Event Name:Annual Corporate Gala 2024
Date:October 15, 2024
Venue:Grand Ballroom, City Convention Center
Chore Task | Assigned To | Due Date | Status
Purchase event invitations and RSVP tracking software | Alex Morgan | Aug 20, 2024 | In Progress
Finalize guest list and send save-the-dates | Jessica Lee | Aug 30, 2024 | Pending
Book catering and menu tasting session | Daniel Kim | Sept 5, 2024 | In Progress
Arrange venue decoration and lighting setup | Sarah Johnson | Sept 10, 2024 | Pending
Coordinate with AV team for sound and video equipment | Michael Brown | Sept 12, 2024 | Pending
Create and distribute event program and signage | Lisa Wong | Sept 18, 2024 | Pending
Conduct final walkthrough and setup rehearsal | James Taylor | Oct 10, 2024 | Pending
Manage on-site event coordination and guest check-in | Tina Patel | Oct 15, 2024 | Pending
Collect feedback forms and post-event survey distribution | Amanda Reyes | Oct 18, 2024 | Pending