## Worksheet
Event Planning Chore Chart - Data Version
Chore Task | Responsible Person | Deadline | Status | Prioritization Level
Venue & Logistics
Book Event Venue | John Doe | 2024-06-15 | In Progress | High
Arrange Permits & Licenses | Jane Smith | 2024-06-18 | Pending | High
Catering & Food Services
Finalize Menu Selection | Sarah Johnson | 2024-06-20 | Not Started | High
Decorations & Aesthetics
Select Theme & Color Scheme | Lisa Brown | 2024-06-12 | Completed | Medium
Guest Management & Invitations
Create Guest List (Final) | Michael Lee | 2024-06-14 | In Progress | High
Technology & Media Support
Arrange AV Equipment Setup | David Wilson | 2024-06-17 | Pending | High
Staffing & Volunteers Coordination
Recruit and Assign Volunteer Roles | Amanda Taylor | 2024-06-13 | Pending | Medium
Timeline & Final Preparations
Final Walkthrough of Venue Layout | John Doe | 2024-06-23 | Pending | High
Budget & Financial Tracking
Review and Approve Final Expenses | Sarah Johnson | 2024-06-25 | Pending | High