## Worksheet
Event Planning Chore Chart
Freelancer Style - Track Tasks & Responsibilities for Seamless Execution
Task | Assigned To | Deadline | Status | Priority
Create Event Concept & Theme | Jane Doe (Creative Lead) | 2023-10-15 | Pending | High
Secure Venue & Book Date | Mark Taylor (Logistics) | 2023-10-18 | In Progress | High
Design Invitations & Branding | Sophia Lee (Designer) | 2023-10-20 | Pending | Medium
Arrange Catering & Menu Approval | Robert Chen (Vendor Coordinator) | 2023-10-17 | In Progress | High
Hire Entertainment (Band/DJ) | Lisa Wong (Entertainment Manager) | 2023-10-16 | Pending | Medium
Coordinate Guest List & RSVPs | Alex Johnson (Admin Assistant) | 2023-10-25 | Pending | Medium
Set Up Event Schedule & Timeline | Jane Doe (Creative Lead) | 2023-10-14 | Completed | High
Finalize Decor & Lighting Plan | Sophia Lee (Designer) | 2023-10-19 | Pending | Medium
Confirm Transportation & Parking | Mark Taylor (Logistics) | 2023-10-21 | Pending | Medium
Conduct Final Walkthrough & Setup Check | Robert Chen (Vendor Coordinator) | 2023-10-24 | Pending | High