## Worksheet
Event Planning Chore Chart
Task | Assigned To | Deadline | Status | Notes/Updates
Venue Booking & Contract Finalization | Event Coordinator | 2023-10-15 | In Progress | Contract draft reviewed, awaiting signature.
Catering Menu Approval | Catering Manager | 2023-10-18 | Not Started | Client preferences to be collected.
Decor & Theme Design | Creative Director | 2023-10-16 | In Progress | Initial concept approved, revisions requested.
Invitation Design & Distribution | Marketing Lead | 2023-10-20 | Not Started | Template pending final review.
Audio-Visual Setup Plan | Technical Coordinator | 2023-10-17 | In Progress | Equipment list compiled; vendor contact pending.
Speaker & Entertainment Booking | Program Manager | 2023-10-14 | Completed | All bookings confirmed; contracts signed.
Staff & Volunteer Scheduling | HR Coordinator | 2023-10-19 | Not Started | Onboarding process underway.
Final Event Run-Through & Rehearsal | Event Director | 2023-10-24 | Not Started | Rehearsal schedule to be confirmed.
Post-Event Feedback Collection | Customer Experience Lead | 2023-10-31 | Not Started | Survey form to be launched post-event.
Budget Reconciliation & Reporting | Finance Manager | 2023-11-05 | Not Started | Final vendor invoices pending.
Last Updated:October 10, 2023 ¦ Version 1.0