## Worksheet
Event Planning Chore Chart
Startup Style ¦ Track Tasks, Assign Responsibilities & Monitor Progress
Task | Assigned To | Deadline | Priority | Status
Finalize event theme & concept | Alice Chen | 2024-06-15 | High | Not Started
Book venue & confirm availability | James Wilson | 2024-06-18 | High | Not Started
Design and print invitations | Sophie Martinez | 2024-06-25 | Medium | In Progress
Secure catering and menu approval | Robert Kim | 2024-06-20 | High | Not Started
Organize entertainment and speakers | Lisa Park | 2024-06-16 | Medium | Not Started
Set up registration and ticketing system | David Liu | 2024-06-19 | High | Not Started
Coordinate logistics and vendor contracts | Emma Taylor | 2024-06-17 | High | Not Started
Create event schedule and timeline | Alice Chen | 2024-06-14 | Medium | Completed
Finalize branding and signage materials | Sophie Martinez | 2024-06-23 | Low | In Progress
Send reminder emails to attendees | James Wilson | 2024-06-30 | Low | Not Started