## Worksheet
Advanced Gantt Chart - Event Planning Template
Task ID | Task Description | Owner | Start Date | End Date
P001 | Define Event Concept & Objectives | Project Manager | 2024-04-05 | 2024-04-15 | 11 | Pending | 0% | None
P002 | Secure Venue & Permits | Logistics Coordinator | 2024-04-16 | 2024-05-15 | 30 | In Progress | 68% | P001
P003 | Develop Marketing Strategy | Marketing Lead | 2024-04-16 | 2024-05-15 | 30 | In Progress | 85% | P001
P004 | Approach & Secure Sponsors | Sponsorship Director | 2024-05-16 | 2024-06-15 | 31 | Pending | 9% | P002, P003
P005 | Design & Produce Event Materials | Design Team Lead | 2024-06-16 | 2024-07-15 | 30 | Pending | 3% | P004
MS01 | Finalize Event Budget & Sponsorship Package | Finance Director | 2024-07-31 | 2024-08-31 | Milestone (End) | Pending | - | P005, P004, P016
P016 | Finalize Event Logistics & Staffing | Operations Manager | 2024-08-01 | 2024-09-30 | Scheduled (61 days) | Pending | -
P017 | Final Event Run-Through & QA | Project Manager | 2024-10-01 | 2024-10-31 | 30 days | Pending | -
MS02 | Event Day: Launch & Execution | Full Team | 2024-11-01 | 2024-11-03 (3 days) | Milestone (Event Day) | -
P018 | Post-Event Debrief & ReportingProject Manager | 2024-11-05 | 2024-11-30 (26 days) | Pending | -
Legend: Progress bars represent completion rate. Red indicates delays, green indicates on track. Milestones highlight key event targets.