## Worksheet
Annual Gantt Chart - Event Planning
Task / Activity | Jan | Feb | Mar | Apr | May | Jun(2 weeks) | Jul(2 weeks) | Aug | Sep | Oct | Nov | Dec
Campaign Planning & Strategy Development | 60%
Vendor & Supplier Negotiation | 100% | 100%
Event Venue Booking & Contract Signing | 100% | 100%
Marketing & Promotional Campaign | 50% | 70%
Logistics & On-site Setup Planning | 30% | 50% | 80%
Speaker & Guest Coordination | 80% | 100% | 100%
Technical & AV System Testing | 20% | 60% | 100%
Event Day Execution & Coordination | 100% | 100%
Post-Event Review & Reporting | Jan | Feb | Mar | Apr | May | Jun(2 weeks) | Jul(2 weeks) | Aug | Sep | Oct | Nov | Dec
Note: Progress bars indicate completion status. All timelines are approximate and subject to change.