## Event Planning Gantt Chart
Task | Start Date | End Date | Duration (Days) | Status
Define Event Goals | 2023-10-01 | 2023-10-05 | 5 | In Progress
Select Venue | 2023-10-06 | 2023-10-12 | 7 | Not Started
Hire Catering Services | 2023-10-13 | 2023-10-15 | 3 | Not Started
Send Invitations | 2023-10-16 | 2023-10-25 | 10 | Not Started
Arrange Entertainment | 2023-10-18 | 2023-10-27 | 10 | Not Started
Finalize Decorations | 2023-10-28 | 2023-11-05 | 9 | Not Started
Event Day Setup | 2023-11-06 | 2023-11-06 | 1 | Not Started
Event Execution | 2023-11-07 | 2023-11-07 | 1 | Not Started
Cleanup & Review | 2023-11-08 | 2023-11-09 | 2 | Not Started