## Worksheet
Event Planning Gantt Chart - Business Use
Task / Activity | Start Date | End Date | Duration (Days) | Progress
Project Kickoff Meeting | 2023-10-01 | 2023-10-01 | 1
Define Event Scope & Objectives | 2023-10-02 | 2023-10-05 | 4
Secure Venue & Permits | 2023-10-06 | 2023-10-15 | 10
Finalize Event Theme & Design | 2023-10-16 | 2023-10-20 | 5
Approve Vendor Contracts | 2023-10-21 | 2023-10-25 | 5
Catering & Menu Finalization | 2023-10-26 | 2023-10-30 | 5
Marketing & Promotion Campaign | 2023-10-31 | 2023-11-15 | 15
Staff & Volunteer Training | 2023-11-16 | 2023-11-18 | 3
Final Event Rehearsal | 2023-11-19 | 2023-11-19 | 1
Event Day - October 20, 2023 | 2023-11-20 | 2023-11-20 | 1
Post-Event Evaluation & Reporting | 2023-11-21 | 2023-11-25 | 5