## Worksheet
Event Planning - Client View Gantt Chart
Task Name | Start Date | End Date | Status | Progress
Venue Booking & Confirmation | 2025-04-01 | 2025-04-10 | In Progress
Catering Selection & Menu Finalization | 2025-04-03 | 2025-04-17 | In Progress
Event Decor & Theme Design Finalization | 2025-04-05 | 2025-04-18 | In Progress
Invitation Design & Distribution | 2025-04-15 | 2025-04-30 | In Progress
DJ/Entertainer Contract Signing | 2025-04-10 | 2025-04-16 | In Progress
Guest Transportation & On-Site Logistics | 2025-04-18 | 2025-04-30 | In Progress
Event Site Walkthrough & Setup Check | 2025-05-14 | 2025-05-16 | Delayed
Main Event Day - Execution | 2025-05-17 | 2025-05-17 | Completed
Client View – Last updated on April 5, 2025 ¦ Project ID: EVT-2025-047