## Worksheet
Event Planning Gantt Chart (Daily)
Task | Start Date | End Date | Duration (Days) | Status
Define Event Objectives | 2024-04-01 | 2024-04-03 | 3 | In Progress
Select Venue & Date | 2024-04-01 | 2024-04-05 | 5 | In Progress
Create Guest List & Send Invitations | 2024-04-06 | 2024-04-15 | 10 | Pending
Arrange Catering & Menu Approval | 2024-04-16 | 2024-04-18 | 3 | Pending
Hire Audiovisual & Decor Team | 2024-04-19 | 2024-04-23 | 5 | Pending
Finalize Schedule & Runthroughs | 2024-04-26 | 2024-04-30 | 5 | Pending
Event Day Coordination & Setup | 2024-05-01 | 2024-05-01 | 1 | Pending
Cleanup & Post-Event Review | 2024-05-02 | 2024-05-03 | 2 | Pending
|  |  |  | 04/01 | 04/02 | 04/03 | 04/04 | 04/05 | 04/06 | 04/07 | 04/08 | 04/09 | 04/10 | ...
Tasks |  |  |  | █ | █ | █
Venue Booking |  |  |  | █████
Invitations |  |  |  | ██████████