## Worksheet
Event Planning Gantt Chart - Dashboard View
Task | Start Date | End Date | Status | Progress
Event Concept & Theme Design | 2024-01-01 | 2024-01-15 | Pending
Venue Booking & Confirmation | 2024-01-10 | 2024-01-31 | Pending
Vendor Contracts (Catering, DJ) | 2024-01-15 | 2024-01-31 | Pending
Guest List & Invitations | 2024-01-20 | 2024-01-31 | Pending
Event Schedule Finalization | 2024-01-25 | 2024-01-31 | Pending
Logistics & Setup Coordination | 2024-01-30 | 2024-02-15 | Pending
Event Day Run-Through & Final Checks | 2024-02-14 | 2024-02-15 | Pending
Event Execution & Management | 2024-02-16 | 2024-02-16 | Pending
Post-Event Review & Feedback | 2024-02-17 | 2024-03-15 | Pending
Dashboard View - Gantt Chart for Event Planning ¦ Last Updated: April 5, 2024