## Worksheet
Event Planning Gantt Chart - Data Version
Task | Start Date | End Date | Status | Duration (Days) | % Complete
Project Kickoff Meeting | 2024-05-10 | 2024-05-10 | Completed | 1 | 100%
Budget Approval | 2024-05-11 | 2024-05-13 | In Progress | 3 | 75%
Venue Booking | 2024-05-14 | 2024-05-18 | In Progress | 5 | 60%
Schedule Guest Speakers | 2024-05-19 | 2024-05-23 | In Progress | 5 | 40%
Promotions & Marketing Launch | 2024-05-24 | 2024-06-15 | Not Started | 23 | 0%
Catering & Menu Finalization | 2024-05-16 | 2024-05-31 | In Progress | 16 | 85%
AV & Technical Setup Plan | 2024-05-20 | 2024-06-18 | In Progress | 30 | 35%
Milestone: Venue Confirmed (Deadline: 2024-05-18)
Milestone: Speakers Finalized (Deadline: 2024-05-31)
Staff & Volunteer Coordination | 2024-06-01 | 2024-06-19 | Not Started | 19 | 0%
Dress Rehearsal & Final Run-through | 2024-06-25 | 2024-06-30 | Not Started | 6 | 0%
Closing & Post-Event Review | 2024-07-01 | 2024-07-15 | Not Started | 15 | 0%
This Gantt Chart is a data version template for event planning. Dates are based on planned timelines. Actual progress may vary.