## Event Planning Gantt Chart
Event Planning Gantt Chart (Detailed)
Task | Start Date | End Date | Duration (Days) | Status | Assigned To
Define Event Objectives & Scope | 2024-01-01 | 2024-01-15 | 15 | In Progress | Jane Smith (PM)
Market & Audience Research | 2024-01-16 | 2024-01-31 | 16 | Pending
Venue Identification & Booking | 2024-02-01 | 2024-03-15 | 45
Budget Development & Approval | 2024-01-01 | 2024-01-31 | 31
Create Marketing & Promotion Plan | 2024-02-01 | 2024-03-31 | 61
Approach Sponsors & Secure Partnerships | 2024-02-15 | 2024-03-31 | 45
Branding, Graphics, and Materials Design | 2024-03-01 | 2024-04-15 | 46
Logistics & Vendor Management (Catering, Tech, etc.) | 2024-03-15 | 2024-06-15 | 93
Set Up Ticketing System & Registration Portal | 2024-04-01 | 2024-05-31 | 61
On-Site Layout & Infrastructure Setup | 2024-06-01 | 2024-06-30 | 31
Dress Rehearsal & Tech Run-Through | 2024-06-25 | 2024-06-30 | 6
EVENT DAY: June 30, 2024 (Final Milestone)