## Worksheet
Event Planning Gantt Chart - Financial View
Task ID | Task Name | Schedule (Weeks) | [5 empty] | Duration (Days) | Budget ($)
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
T1 | Initial Planning & Requirements | [6 empty] | 7 | $2,500
T2 | Venue Booking & Site Inspection | [6 empty] | 14 | $8,750
T3 | Catering Contract Finalization | [6 empty] | 7 | $6,200
T4 | Marketing & Promotion Campaign | [6 empty] | 21 | $7,800
T5 | Event Staff Recruitment & Training | [5 empty] | 14 | $5,900
T6 | Technology & Audio-Visual Setup | [5 empty] | 14 | $9,250
M1 | Final Event Briefing (Go/No-Go) | [5 empty] | 1 | $5,000
T7 | Event Execution & Live Management | [5 empty] | 4 | $35,500
T8 | Post-Event Review & Reporting | [5 empty] | 3 | $4,800
Total Budget: | [9 empty] | $96,700
Legend:
Progress- Task in progress
Milestone- Key milestone reached
Execution- Event day activities
Post-Event- Post-event phase