## Worksheet
Event Planning Gantt Chart - Home Use
Task | Start Date | End Date | Status | % Complete
Define Event Purpose & Theme | 2024-03-15 | 2024-03-18 | In Progress | 75%
Book Venue & Confirm Availability | 2024-03-19 | 2024-03-25 | In Progress | 60%
Create Guest List & Send Invitations | 2024-03-26 | 2024-04-15 | Not Started | 0%
Select and Confirm Catering Service | 2024-03-27 | 2024-04-10 | In Progress | 50%
Plan and Order Decorations | 2024-03-30 | 2024-04-18 | Not Started | 0%
Hire Performers or DJ/Entertainment Team | 2024-04-01 | 2024-04-15 | Not Started | 0%
Milestone: Final RSVP Deadline | 2024-04-15 | 2024-04-15 | Upcoming | —
Arrange Transportation & Parking | 2024-04-16 | 2024-05-10 | Not Started | 0%
Final Venue Walkthrough & Setup Check | 2024-05-18 | 2024-05-19 | Not Started | 0%
Milestone: Event Day - Celebration! | 2024-05-20 | 2024-05-20 | Upcoming | —
Note: This is a home-use template for personal event planning. Customize dates and tasks as needed.