## Worksheet
Event Planning Gantt Chart - Large Business Style
Task / Activity | Start Date | End Date | Duration (Days) | Responsible Team | Status / Progress
Phase 1: Event Concept & Strategy | Jan 5, 2024 | Jan 20, 2024 | 15 | Executive Team
Define Objectives & KPIs | Jan 5, 2024 | Jan 8, 2024 | 3 | Strategic Planning Group
Budget Approval & Allocation | Jan 9, 2024 | Jan 15, 2024 | 6 | Finance Department
Finalize Event Theme & Branding | Jan 16, 2024 | Jan 20, 2024 | 5 | Marketing & Design Team
Phase 2: Venue & Logistics | Jan 21, 2024 | Feb 15, 2024 | 36 | Logistics Team
Venue Selection & Booking | Jan 21, 2024 | Feb 5, 2024 | 15 | Logistics Team
Catering & Hospitality Arrangements | Jan 28, 2024 | Feb 10, 2024 | 13 | Catering Services Team
Transportation & Accommodation | Feb 1, 2024 | Feb 15, 2024 | 14 | Travel Coordination Unit
Phase 3: Marketing & Promotion | Feb 16, 2024 | Apr 5, 2024 | 50 | Marketing Department
Develop Marketing Campaign | Feb 16, 2024 | Mar 5, 2024 | 17 | Creative Team
Social Media & Email Outreach | Mar 6, 2024 | Apr 5, 2024 | 31 | Digital Marketing Team
Media Relations & Press Releases | Mar 10, 2024 | Apr 5, 2024 | 31 | PR Team
Phase 4: On-Site Execution | Apr 6, 2024 | May 15, 2024 | 40 | Event Operations Team
Site Setup & Infrastructure | Apr 6, 2024 | Apr 30, 2024 | 25 | Operations Crews
Technical & AV Installation | Apr 10, 2024 | May 5, 2024 | 36 | AV Technicians
Staff & Volunteer Training | Apr 25, 2024 | May 10, 2024 | 16 | HR & Operations Team
Phase 5: Event Delivery | May 16, 2024 | May 18, 2024 | 3 | All Teams (Critical)
Event Day: May 16, 2024 (Live) | May 16, 2024 | May 16, 2024 | 1 | Crisis Management Team
Event Wrap-Up & Debrief | May 17, 2024 | May 18, 2024 | 2 | All Teams (Critical)
Post-Event Activities | May 19, 2024 | Jun 30, 2024 | 43 | Analytics & Finance Teams
Performance Analysis & Reporting | May 19, 2024 | Jun 10, 2024 | 23 | Data Analytics Team
Stakeholder Feedback Collection | May 20, 2024 | Jun 5, 2024 | 17 | Customer Experience Team