## Worksheet
Event Planning - Manager View Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress Timeline
#001 | Initial Planning & Scope Definition | 2025-04-05 | 2025-04-12 | 7 | In Progress
#002 | Vendor Selection & Contracting | 2025-04-13 | 2025-04-18 | 6 | In Progress
#003 | Event Venue Booking | 2025-04-14 | 2025-04-19 | 6 | In Progress
#004 | Marketing & Promotion Campaign | 2025-04-16 | 2025-05-17 | 31 | In Progress
#005 | Staffing & Volunteer Coordination | 2025-04-17 | 2025-04-30 | 14 | In Progress
#006 | Technical Setup & Equipment Delivery | 2025-05-18 | 2025-05-31 | 14 | To Do
#007 | Event Rehearsal & Dry Run | 2025-06-01 | 2025-06-14 | 14 | To Do
Final Event Day |  | 2025-06-15 | 2025-06-15 | 1 | Milestone
#008 | Post-Event Evaluation & Reporting | 2025-06-16 | 2025-06-31 | 15 | To Do
Legend:
●Progress bar indicates task completion percentage
●Milestone - Key event date with no duration