## Worksheet
Event Planning Gantt Chart - Page 1
Task ID | Task Description | Start Date | End Date | Duration (Days) | Status | Timeline (Weeks)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6
T01 | Define Event Objectives | 2023-10-01 | 2023-10-05 | 5 | Pending
T02 | Secure Venue | 2023-10-06 | 2023-10-15 | 10 | In Progress
T03 | Invite Key Stakeholders | 2023-10-16 | 2023-10-25 | 10 | Pending
M01 | Finalize Budget Approval | 2023-10-30
T04 | Design Marketing Materials | 2023-11-01 | 2023-11-15
T05 | Book Catering Services | 2023-11-16
2023-11-3015Pending
Page 1 of 3
Event Planning Gantt Chart - Page 2
Task ID | Task Description | Start Date | End Date | Duration (Days) | Status | Timeline (Weeks)
|  | W7 | W8 | W9 | W10 | W11
T06 | Hire Event Staff | 2023-12-012023-12-1414In Progress
T07 | Finalize Program Schedule | 2023-12-15 | 2023-12-3117Pending
T08 | Coordinate AV & Tech Setup | 2024-01-01 | 2024-01-1515Pending
M02 | Event Planning Kickoff Meeting | 2024-01-16
T09 | Conduct Rehearsal | 2024-01-17 | 2024-01-3115Pending
Page 2 of 3
Event Planning Gantt Chart - Page 3
Task ID | Task Description | Start Date | End Date
|  |  |  | PendingW12 | W13
T10 | Send Final Invitations | 2024-02-012024-02-155 | In Progress
T11 | Onsite Event Setup | 2024-02-16 | 2024-02-385Pending
M03 | Event Day - Launch | 2024-03-01
T12 | Post-Event Feedback Collection | 2024-03-05 | 2024-03-1511Pending
T13 | Final Report & Debrief | 2024-03-16 | 2024-03-3116Pending
Page 3 of 3