## Event Planning Gantt Chart
Event Planning Gantt Chart
Task | Start Date | End Date | Status | Responsible Person
Define Event Goals & Theme | 2023-10-01 | 2023-10-05 | In Progress | Alice Johnson
Secure Venue & Date | 2023-10-06 | 2023-10-15 | Pending | Bob Smith
Plan Budget & Allocate Funds | 2023-10-07 | 2023-10-18 | In Progress | Cara Lee
Invite Attendees & Send Invitations | 2023-10-16 | 2023-10-30 | Pending | Daniel Kim
Coordinate Catering & Entertainment | 2023-10-19 | 2023-11-05 | Pending | Elena Garcia
Finalize Event Schedule & Timeline | 2023-11-01 | 2023-11-07 | Pending | Franklin Brown
Conduct Event Rehearsal | 2023-11-08 | 2023-11-09 | Pending | Gina Patel
Execute Event Day Plan | 2023-11-10 | 2023-11-10 | Pending | All Team Members
Post-Event Feedback & Report | 2023-11-11 | 2023-11-15 | Pending | Alice Johnson