## Event Planning Gantt Chart
Event Planning Gantt Chart
Task | Start Date | End Date | Status | % Complete
Define Event Goals & Objectives | 2024-01-05 | 2024-01-15 | In Progress | 75%
Budget Planning & Approval | 2024-01-16 | 2024-01-31 | In Progress | 85%
Secure Event Venue | 2024-02-01 | 2024-02-15 | Pending | 35%
Vendor Contracts (Catering, AV, etc.) | 2024-02-16 | 2024-03-15 | Pending | 15%
Create Event Branding & Design | 2024-03-16 | 2024-03-31 | Pending | 5%
Launch Registration Portal | 2024-04-01 | 2024-04-30 | Pending | 5%
Email Campaigns & Promotions | 2024-05-01 | 2024-06-15 | Pending | 0%
Milestone: Finalize Attendee List | 2024-06-15 | 2024-06-15 | Complete | 100%
Setup & Rehearsal Schedule | 2024-07-15 | 2024-07-31 | Pending | 5%
Milestone: Event Day (Main Program) | 2024-08-01 | 2024-08-01 | Pending | 5%
Post-Event Survey & Feedback Collection | 2024-08-02 | 2024-08-15 | Pending | 5%
Milestone: Final Report & Evaluation | 2024-08-31 | 2024-08-31 | Pending | 5%
Printable Gantt Chart for Event Planning ¦ Generated on 2024-01-05