## Event Planning Gantt Chart
Event Planning Gantt Chart
Task | Start Date | End Date | Duration (Days) | Status | Progress
Phase 1: Planning & Preparation
Define Event Objectives | 2024-04-01 | 2024-04-05 | 5 | Completed
Set Budget Allocation | 2024-04-03 | 2024-04-15 | 13 | In Progress
Form Event Committee | 2024-04-01 | 2024-04-10 | 10 | Completed
Phase 2: Logistics & Coordination
Secure Venue | 2024-04-15 | 2024-05-15 | 30 | In Progress
Book Catering & Entertainment | 2024-05-01 | 2024-05-31 | 31 | Delayed
Phase 3: Marketing & Communication
Create Event Promotions | 2024-05-10 | 2024-06-15 | 37 | In Progress
Phase 4: Final Preparations
Finalize Guest List | 2024-06-15 | 2024-07-15 | 30 | In Progress
Phase 5: Event Execution & Follow-Up
Event Day Management | 2024-07-15 | 2024-07-15 | 1 | Delayed
Post-Event Feedback & Report | 2024-07-16 | 2024-07-31 | 16 | Delayed
Total Duration | 2024-04-01 to 2024-07-31 |  | 123 Days | Overall Progress: 68%
Legend:Completed (Green) ¦ In Progress (Orange) ¦ Delayed (Red)