## Worksheet
Event Planning Gantt Chart - Report Version
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress Timeline
TP001 | Define Event Objectives | 2023-10-05 | 2023-10-12 | 8 | Completed
TP002 | Secure Venue Booking | 2023-10-15 | 2023-11-05 | 21 | Completed
TP003 | Design Event Theme & Layout | 2023-11-15 | 2024-01-15 | 61 | Delayed
TP004 | Invite Key Stakeholders | 2024-01-20 | 2024-01-31 | 12 | Completed
TP005 | Finalize Catering & Logistics | 2024-02-15 | 2024-03-18 | 31 | Completed
TP006 | Event Day Coordination | 2024-03-19 | 2024-03-19 | 1 | Completed
TP007 | Post-Event Review & Report | 2024-03-25 | 2024-04-15 | 21 | Delayed
M001 | Event Launch Date | 2024-03-19 | 2024-03-19 | 1 | Completed
Total Duration: |  |  |  | 234 | Overall Progress: 76%
Report Version - Generated on 2023-10-25 ¦ All dates are in YYYY-MM-DD format