## Worksheet
Small Business Event Planning Gantt Chart
Task | Start Date | End Date | Duration (Days) | Status | Progress
Define Event Objective | 2024-01-15 | 2024-01-18 | 3 | Completed
Book Venue | 2024-01-19 | 2024-01-25 | 7 | In Progress
Invite Guests | 2024-01-26 | 2024-01-31 | 6 | Not Started
Arrange Catering | 2024-01-27 | 2024-01-30 | 4 | Not Started
Hire Entertainment | 2024-01-28 | 2024-01-31 | 4 | Not Started
Set Up Decorations | 2024-01-31 | 2024-02-01 | 2 | Not Started
Final Run-Through | 2024-02-01 | 2024-02-01 | 1 | Not Started
Event Day | 2024-02-02 | 2024-02-03 | 1 | Not Started
Post-Event Review | 2024-02-04 | 2024-02-05 | 2 | Not Started
© 2024 Small Business Event Planning ¦ Gantt Chart Template