## Worksheet
Event Planning Gantt Chart - Startup Style
Task | Start Date | End Date | Duration (Days) | Status | Progress
Define Event Goals | 2024-03-01 | 2024-03-05 | 5 | Completed
Select Venue | 2024-03-06 | 2024-03-15 | 10 | In Progress
Invite Guests | 2024-03-16 | 2024-03-30 | 15 | In Progress
Plan Agenda & Speakers | 2024-03-18 | 2024-03-25 | 8 | In Progress
Coordinate Logistics | 2024-03-26 | 2024-04-10 | 15 | Delayed
Marketing & Promotion | 2024-03-20 | 2024-04-15 | 26 | In Progress
Finalize Budget | 2024-03-31 | 2024-04-05 | 6 | In Progress
Event Day Execution | 2024-04-16 | 2024-04-16 | 1 | Delayed
Last Updated: March 5, 2024 ¦ Version v1.0