## Worksheet
Event Planning - Gantt Chart Summary View
Task Name | Start Date | End Date | Duration (Days) | Status
Phase 1: Event Planning | - | - | - | Planned
Define Event Objectives & Scope | 2024-04-01 | 2024-04-05 | 5 | In Progress
Phase 2: Vendor Selection | - | - | - | Planned
Secure Catering Provider | 2024-04-06 | 2024-04-15 | 10 | In Progress
Phase 3: Venue Booking | - | - | - | Planned
Finalize Venue Contract & Deposit | 2024-04-16 | 2024-04-30 | 15 | Not Started
Phase 4: Marketing & Promotion | - | - | - | Planned
Launch Event Website & Registration Portal | 2024-05-01 | 2024-05-15 | 15 | Not Started
Phase 5: On-Site Coordination | - | - | - | Planned
Finalize Event Schedule & Speakers | 2024-05-16 | 2024-05-31 | 16 | Not Started
Milestone: Event Day | 2024-06-01 | 2024-06-01 | 1 | Not Started
Phase 6: Post-Event Review | - | - | - | Planned
Collect Feedback & Analyze Results | 2024-06-02 | 2024-06-15 | 14 | Not Started
Legend:
-Milestoneindicates a key event with no duration.