## Team Event Planning Gantt Chart
Team Event Planning Gantt Chart
Task | Owner | Start Date | End Date | Status | Progress (%)
Ceremony Planning & Venue Booking | Anna Smith | 2024-03-01 | 2024-03-15 | In Progress
Guest List & Invitations | James Lee | 2024-03-05 | 2024-03-18 | In Progress
Food & Beverage Coordination | Lisa Tran | 2024-03-10 | 2024-03-25 | To Do
Entertainment & Music Setup | David Chen | 2024-03-15 | 2024-03-31 | To Do
Logistics & Transportation Arrangements | Sophie Williams | 2024-03-12 | 2024-03-28 | In Progress
Decor & Setup Design | Maria Garcia | 2024-03-08 | 2024-03-27 | In Progress
Event Schedule & Timeline Finalization | Robert Kim | 2024-03-25 | 2024-03-31 | To Do
Final Run-through & Rehearsal | Aisha Patel | 2024-04-01 | 2024-04-05 | To Do
Post-Event Feedback Collection | Carlos Mendez | 2024-04-10 | 2024-04-15
Overall Project Status |  |  |  |  | 68%
Last updated: March 20, 2024 ¦ Team Use Template