## Event Planning Gantt Chart
Event Planning Gantt Chart
Task | Start Date | End Date | Duration (Days) | Status | Progress (%)
Project Initiation | 2023-10-01 | 2023-10-05 | 5 | In Progress
Theme Development | 2023-10-06 | 2023-10-15 | 10 | In Progress
Vendor Contracts | 2023-10-10 | 2023-10-25 | 16 | Pending
Marketing Campaign | 2023-10-15 | 2023-11-10 | 27 | Pending
Event Logistics Setup | 2023-10-20 | 2023-11-15 | 26 | Pending
Final Rehearsal | 2023-11-16 | 2023-11-17 | 2 | Pending
Event Day Execution | 2023-11-18 | 2023-11-18 | 1 | Pending
Post-Event Review | 2023-11-19 | 2023-11-25 | 7 | Pending
Template Version:1.0 ¦Purpose:Event Planning ¦Style/Version:Gantt Chart