## Worksheet
Event Planning Gantt Chart - Tracking View
Task | Start Date | End Date | Duration (Days) | Status | Progress
Planning Phase | 2024-03-01 | 2024-03-15 | 15 | On Track
Venue Booking & Site Inspection | 2024-03-01 | 2024-03-15 | 15 | On Track
Vendor Contracts (Catering, Decor, AV) | 2024-03-16 | 2024-03-31 | 16 | On Track
Marketing & Promotion Campaign | 2024-03-16 | 2024-04-15 | 31 | On Track
Finalize Guest List & Invitations | 2024-03-16 | 2024-04-15 | 31 | Delayed
Logistics & Transport Coordination | 2024-04-16 | 2024-05-15 | 30 | On Track
Event Rehearsal & Tech Check | 2024-05-16 | 2024-05-17 | 2 | On Track
Event Day | 2024-05-18 | 2024-05-18 | 1 | Milestone (Completed)
Post-Event Wrap-Up & Feedback Collection | 2024-05-19 | 2024-05-31 | 13 | Completed
Legend:
●Completed Tasks
●On Track Progress
●Delayed Tasks