## Event Planning - Habit Tracker
Event Planning - Habit Tracker (Personal Use)
Date | Task / Habit | Planned? | Status | Notes
2024-05-01 | Create Guest List | ✓ | Completed | Finalized 35 names, sent invites.
2024-05-01 | Book Venue | ✓ | Completed | Venue confirmed for June 15th.
2024-05-02 | Check Catering Options | ✓ | In Progress | Scheduled tasting next week.
2024-05-03 | Design Invitations | ✓ | In Progress | Draft approved by partner.
2024-05-04 | Confirm Audio/Visual Setup | ✓ | Pending | Contacting technician.
2024-05-05 | Send Reminders to Guests | ✓ | Pending | Scheduled for Friday.
2024-05-06 | Finalize Decor Theme | ✓ | Pending | Review mood board.
2024-05-07 | Confirm RSVPs | ✓ | Pending | Awaiting replies from 8 guests.
2024-05-08 | Arrange Transportation | ✓ | Pending | Contacting shuttle service.
2024-05-09 | Finalize Schedule of Events | ✓ | Pending | To be reviewed with team.
* This template is for personal use in event planning and habit tracking. Customize as needed.