## Worksheet
Event Planning - Habit Tracker Report
Period: January 2025 - December 2025 ¦ Prepared on: April 5, 2025
Week | Planning Task | Target Completion Date | Status | Habit Score (1-5) | Notes/Remarks
Week 1 | Define Event Theme & Objectives | Jan 8, 2025 | Completed | 5 | Met with team; finalized theme "Summer Soirée 2025"
Week 1 | Select Venue & Book Date | Jan 10, 2025 | Completed | 4 | Venue confirmed: Riverside Pavilion; slight delay in contract signing.
Week 2 | Create Guest List & Send Invitations | Jan 15, 2025 | Completed | 5 | Email invitations sent with RSVP link; response rate: 93%
Week 3 | Negotiate Vendor Contracts (Catering, Music) | Jan 22, 2025 | In Progress | 3 | Caterer agreement in final review; music band contract pending.
Week 4 | Design & Print Invitations + Decor Plans | Jan 29, 2025 | Pending | NA | Scheduled for next week; design finalized.
Week 5 | Finalize Budget & Track Expenses | Feb 5, 2025 | Pending | NA | Budget spreadsheet updated; no overspending.
Week 6 | Coordinate Volunteer Assignments | Feb 12, 2025 | Pending | NA | Volunteer sign-up form live; recruitment ongoing.
Week 7 | Send Reminder Emails to Guests | Feb 19, 2025 | Pending | NA | Scheduled for Friday; auto-reminder set.
Week 8 | Conduct Final Rehearsal & Setup Test | Feb 26, 2025 | Pending | NA | In planning; venue access secured.
Week 9 | Confirm Vendor Deliveries & Timings | Mar 5, 2025 | Pending | NA | Progress Summary (as of March 2025)
Total Completed Tasks: |  |  |  | 3/10 | Target: 8/10 by end of March
Average Habit Score: |  |  |  | 4.2 | Good consistency with task execution