## Event Planning - Home Template
Event Planning - Home Template (Multi-Page)
Event Name | Date | Location | Guest Count | Status | Notes
Birthday Party | 2025-04-15 | Green Valley Gardens | 50 | Pending | Send invites by March 1st.
Celebration Gala | 2025-06-20 | Royal Plaza Ballroom | 150 | Confirmed | Dinner and live band confirmed.
Corporate Retreat | 2025-08-10 | Meadow Ridge Resort | 75 | In Planning | Schedule team workshop sessions.
Wedding Ceremony | 2025-09-30 | Beachside Pavilion | 120 | Pending Approval | Bridal party and floral arrangements in progress.
New Year’s Eve Party | 2026-01-01 | City Center Plaza | 300 | Planning Phase | Budget proposal under review.
Anniversary Dinner | 2025-11-18 | Fine Dining Restaurant, Downtown | 8 | Scheduled | Celebration cake and reservations made.
Page 1 of 3¦ Template Type: Home Template ¦ Purpose: Event Planning
Event Budget Summary (Page 2)
Category | Planned Budget | Actual Spend | Budget Variance | Status
Decorations & Theme | $3,500 | $3,200 | + $300 (Under Budget) | On Track
Catering & Beverages | $15,000 | $14,850 | + $150 (Under Budget) | On Track
Entertainment & DJ | $2,800 | $2,950 | - $150 (Over Budget) | Needs Review
Marketing & Invitations | $1,200 | $1,320 | - $120 (Over Budget) | Needs Review
Travel & Accommodations | $4,500 | $4,100 | + $400 (Under Budget) | On Track
Total | $27,000 | $26,420 | + $580 (Under Budget) | Overall: On Track
Page 2 of 3¦ Template Type: Home Template ¦ Purpose: Event Planning
Task Assignments & Milestones (Page 3)
Task | Owner | Due Date | Status
Finalize Guest List | Sarah Johnson (Coordinator) | 2025-03-10 | Completed
Book Venue & Confirm Availability | Liam Chen (Event Lead) | 2025-01-31 | Completed
Order Invitations & Send Out | Maria Lopez (Logistics) | 2025-02-15 | Pending
Create Event Timeline & Schedule | James Wilson (Project Manager) | 2025-04-01 | In Progress
Finalize Catering Menu & Taste Test | Emma Brown (Catering Director) | 2025-04-30 | In Planning
Total Tasks: 6 ¦ Completed: 2 ¦ In Progress: 1 ¦ Pending: 3 | Progress Overview
Page 3 of 3¦ Template Type: Home Template ¦ Purpose: Event Planning