## Event Planning - Tracking View
Event Planning - Tracking View (Home Template)
Event Overview
Event Name | Date & Time | Location | Guest Count | Budget (USD) | Status | Actions
Annual Company Gala | 2023-11-15 6:00 PM - 11:00 PM | Symphony Hall, Downtown | 350 | $25,000 | Planned | Edit¦Delete
Product Launch Party | 2023-10-28 5:30 PM - 9:00 PM | Innovate Center, Tech District | 180 | $15,500 | In Progress | Edit¦Delete
Team Building Retreat | 2023-12-05 8:00 AM - 6:00 PM | Pine Ridge Lodge, Mountain Area | 45 | $8,750 | Delayed | Edit¦Delete
Project Timeline & Key Milestones
Milestone | Target Date | Actual Date | Status | Owner | Notes/Updates
Finalize Guest List | 2023-10-15 | 2023-10-14 | Completed | Jane Smith | Confirmed 98% of invitees.
Secure Venue & Catering | 2023-09-30 | - | In Progress | Mike Johnson | Negotiations ongoing with two vendors.
Send Invitations | 2023-10-25 | - | Overdue | Sarah Lee | Delay due to updated guest list.
Budget Tracker
Category | Budget (USD) | Spent (USD) | Remaining (USD) | Percentage Used
Venue & Facilities | $8,000 | $7,850 | $150
Catering & Drinks | $6,500 | $4,200 | $2,300
Marketing & Promotion | $3,500 | $1,200 | $2,300
Entertainment & Activities | $4,500 | $2,900 | $1,600
Final Summary & Notes
Total Projected Budget:$25,000 Total Spent to Date:$16,150 Overall Status:On Track (with minor delays in invitations) Next Steps: Finalize catering contracts by October 20. Send out final invitation reminders on October 26. Conduct a team walkthrough at the venue on November 1st.