## Worksheet
Event Planning Inventory - Planning View
Inventory Management for Upcoming Events ¦ Version: 1.0 ¦ Updated: October 2024
Item ID | Category | Description | Quantity Required | Current Stock | Status | Responsible Team Member | Date Needed By (Planned)
Venue & Facilities
VEN-001 | Venue Booking | Conference Hall - Main Auditorium (Capacity: 500) | 1 | 1 | Completed | Event Coordination Team | 2024-11-30
Equipment & Technology
EQP-012 | Audio/Visual | Professional Sound System (Microphones, Speakers, Mixer) | 1 Set | 0 | Pending Order | Digital Media Team | 2024-11-25
EQP-033 | Projection & Screens | High-Resolution Projector + 8x10 ft Screen | 1 Unit | 2 | Completed (On Hand) | Digital Media Team | 2024-11-30
Supplies & Materials
SUP-205 | Stationery & Print | Event Program Books (500 Copies) | 500 | 187 | Partial Order Placed | Print Team Lead | 2024-11-28
SUP-701 | Catering Supplies | Dinnerware, Glassware, Cutlery (500 Sets) | 500 Sets | 423 | Pending Delivery | Catering Manager | 2024-11-30
Personnel & Logistics
PER-889 | Staffing | Event Security Personnel (12 Staff) | 12 | 0 | Not Confirmed | Hiring Coordinator | 2024-11-20
Miscellaneous & Contingencies
MIS-990 | Emergency Kit | First Aid Supplies, Flashlights, Extension Cords | 1 Kit | 3 | Completed (On Hand) | Safety Officer | 2024-11-30
Total Items: |  |  | 10 | 723 | Status Summary: |  | Pending: 4 ¦ Completed: 5 ¦ Delayed: 1
Legend:🟢 Completed🟡 Pending Order/Planned🔴 Delayed/Not Confirmed
This template is designed for event planning inventory tracking with a clear planning view layout. Export to Excel for dynamic filtering and reporting.