## Worksheet
Event Planning - Maintenance Log - Analysis View
Task ID | Equipment/Asset | Maintenance Type | Date Scheduled | Date Performed | Status | Technician Assigned | Notes / Observations
MNT-2024-001 | Audio System - Main Stage | Preventive Maintenance | 2024-06-15 | 2024-06-15 | Completed | Alex Turner | Replaced faulty cables; system tested successfully.
MNT-2024-002 | Lighting Rig - Stage Left | Inspection & Calibration | 2024-06-17 | - | Pending | Sarah Chen | Requires check for flickering LED panels.
MNT-2024-003 | Projector - Main Screen | Deep Cleaning & Alignment | 2024-06-18 | 2024-06-19 | Completed | Daniel Moore | Cleaned lens filter; re-aligned image focus.
MNT-2024-004 | Power Distribution Unit (PDU) | Overhaul & Safety Check | 2024-06-13 | 2024-06-13 | Completed | Linda Park | Checked load capacity; replaced worn connectors.
MNT-2024-005 | Stage Flooring - Main Area | Structural Inspection | 2024-06-16 | - | Overdue | Jamal Brooks | Due on 2024-06-15; delayed due to scheduling conflict.
MNT-2024-006 | Sound Booth Equipment | Calibration & Testing | 2024-06-19 | - | Pending | Nina Patel | Waiting for audio engineer availability.
MNT-2024-007 | Backstage HVAC Unit | Filter Replacement & Vent Cleaning | 2024-06-14 | 2024-06-15 | Completed | Cameron Lee | New filters installed; airflow improved.
MNT-2024-008 | Emergency Lighting System | Functional Test & Battery Check | 2024-06-11 | 2024-06-11 | Completed | Elena Martinez | All units passed test; batteries replaced in 3 zones.
Total Tasks: |  |  |  |  | 8 | Completed: 5 ¦ Pending: 2 ¦ Overdue: 1