## Worksheet
Event Planning - Order Tracker (Manager View)
Order ID | Event Name | Client Name | Date & Time | Service Type | Total Amount ($) | Status | Action Status (ETA) | Manager Notes
ORD-001 | Corporate Gala 2024 | Sarah Johnson (TechNova Inc.) | 2024-11-15 @ 6:00 PM | Venue & Catering Package A | 8,500.00 | Pending Approval | 12/3/24 (Due)Review by Finance Team | Awaiting final sign-off. Ensure catering menu is confirmed before Nov 30.
ORD-002 | Annual Charity Fundraiser | Michael Thompson (Hope Foundation) | 2024-11-30 @ 5:30 PM | Full Event Package (Catering, Decor, Sound) | 12,750.00 | Completed - Delivered | All items delivered on time. Client feedback positive.
ORD-003 | Product Launch: NovaWave X1 | Linda Chen (Innovatech) | 2024-12-15 @ 4:00 PM | Presentation & Tech Setup + Lighting | 6,300.00 | In Progress (Setup) |  | Stage build started. Final equipment check scheduled for Dec 14.
ORD-004 | Winter Wedding Ceremony | Ryan & Emily (Harrison Family) | 2025-01-18 @ 3:30 PM | Celebration Package w/ Floral, Music & Cake | 9,450.00 | Delayed (Due to Supplier) | Floral delivery delayed by 3 days. Rebooked with backup vendor.
ORD-005 | Seminar: Leadership in Digital Age | David Reed (FutureLeaders Inc.) | 2024-12-18 @ 9:00 AM | Conference Package (AV, Seating, Coffee) | 3,800.00 | Pending Final Payment |  | Payment pending confirmation from client.
ORD-006 | New Year’s Eve Countdown Party | Celebrity Events Ltd. | 2025-12-31 @ 8:30 PM | Large-Scale Event (Fireworks, DJ, Security) | 24,500.00 | Under Review | Final budget approval pending from finance.