## Worksheet
Personal Finance Tracker - Event Planning (Financial View)
Category | Planned Budget ($) | Actual Spend ($) | Remaining ($) | Status | Action Required
Event Planning Expenses
Venue Rental | 2,500.00 | 2,350.00 | 150 | On Track | N/A
Catering Services | 3,200.00 | 3,150.00 | 50 | On Track | N/A
Decorations & Theme | 1,200.00 | 1,320.00 | -120 | Over Budget | Review vendor contract
Entertainment (DJ/Band) | 1,500.00 | 1,450.00 | 50 | On Track | N/A
Photography & Videography | 2,000.00 | 1,980.00 | 20 | On Track | N/A
Invitations & Stationery | 600 | 580 | 20 | On Track | N/A
Miscellaneous Expenses | 500 | 625 | -125 | Over Budget | Review purchases for necessity
Total Event Expenses | 11,500.00 | 11,455.00 | 45 | On Track | N/A
Event Budget Summary & Financial Status
Budgeted Total (Planned) | 11,500.00 |  |  | Actual Total Spend | 11,455.00
Total Remaining Budget | 45 |  |  | Budget Variance | -45.00 (Under)
Notes & Recommendations
- All primary event categories are within budget except for Decorations and Miscellaneous. - Consider reallocating remaining funds from under-spent categories to cover overages. - Finalize all vendor contracts before the next payment milestone.