## Worksheet
Event Planning - Detailed Planner Template
Date & Time | Event Phase | Task Details |  |  | Responsible Party | Status
|  | Task Description | Deadline | Notes / Instructions
PHASE 1: PLANNING & PREPARATION (4-6 Weeks Before)
8 weeks before | Initial Planning | Define event purpose, theme, and expected attendance | 12/01/2024 | Create mission statement and success metrics | Event Coordinator | Pending
6 weeks before | Budget Planning | Develop detailed budget with line items for venue, catering, decor, etc. | 12/08/2024 | Include contingency fund (10%) | Finance Lead | Pending
6 weeks before | Venue Booking | Select and contract venue based on capacity, location, and availability | 12/08/2024 | Confirm AV equipment availability and setup requirements | Venue Manager | Pending
PHASE 2: LOGISTICS & COORDINATION (3-4 Weeks Before)
4 weeks before | Catering & Menu Finalization | Select catering provider and finalize menu with dietary options | 12/29/2024 | Confirm allergy accommodations and serving time schedule | Catering Coordinator | Pending
3 weeks before | Invitations & RSVP Tracking | Design, print, and send digital invitations; set up RSVP tracking system | 01/05/2025 | Add deadline for responses; include travel accommodations info if needed | Marketing Lead | Pending
PHASE 3: FINAL PREPARATIONS (1 Week Before)
1 week before | Final Vendor Confirmations | Contact all vendors for final confirmation of deliverables and setup times | 01/24/2025 | Verify contact details, insurance documentation, and payment status | Operations Manager | Pending
PHASE 4: DAY-OF EXECUTION (Event Day)
01/26/2025 8:00 AM | Setup & Installation | Arrive at venue to begin setup of tables, chairs, signage, decor | N/A | Coordinate with vendors for equipment delivery and installation | Setup Crew Lead | Pending
01/26/2025 11:00 AM | Ceremony / Main Event Start | Begin official event program (speeches, presentations, etc.) | N/A | Ensure audiovisual systems are tested and running smoothly | Event Host & Tech Team | Pending
PHASE 5: POST-EVENT (After Event)
01/26/2025 4:00 PM | Cleanup & Breakdown | Begin dismantling decorations, packing equipment, and removing trash | N/A | Ensure all rented items are returned in good condition | Cleanup Crew Lead | Pending
02/01/2025 | Post-Event Report & Debrief | Compile feedback, financial summary, and lessons learned report | 02/01/2025 | Distribute to stakeholders for review and future planning reference | Project Manager | Pending
SUMMARY: Total Tasks - 10 ¦ Completed - 0 ¦ In Progress - 0 ¦ Pending - 10
Notes: Use this template as a master checklist. Update the "Status" column daily during the planning phase. Adjust dates and responsibilities as needed based on your specific event.