## Worksheet
Event Planning Planner - Office Use
Event Details
Event Name | Date & Time | Location | Attendees (Est.) | Status
Upcoming Events
Annual Company Retreat | 2024-05-15 9:00 AM - 4:30 PM | Grand Mountain Lodge, 123 Summit Way | 85 | Scheduled
Q2 Product Launch | 2024-06-03 1:00 PM - 3:30 PM | Main Conference Room, Building A | 45 | Confirmed
Planned for Future
Summer Networking Mixer | 2024-08-17 6:00 PM - 9:00 PM | Skyline Rooftop, Downtown | 65 | Pending Approval
Client Appreciation Dinner | 2024-10-10 7:00 PM - 10:30 PM | Parkview Fine Dining, 55 Fifth Ave | 32 | To Be Scheduled
Summary (Total Events: 4)
Event Planning Checklist
Task | Responsible Party | Due Date | Status | Notes
Core Planning Tasks
Define event objectives and KPIs | Marketing Team Lead | 2024-04-15 | Completed | Goals documented in project folder.
Select and confirm venue booking | Operations Manager | 2024-04-30 | In Progress | Contract pending signature.
Logistics & Coordination
Arrange catering and refreshments | Catering Coordinator | 2024-05-01 | Not Started | Vendor selection in progress.
Coordinate audiovisual equipment setup | IT Support Specialist | 2024-05-10 | Not Started | Check availability of projectors and microphones.
Promotion & Communication
Send out event invitations | HR Coordinator | 2024-05-08 | Not Started | Draft pending approval.
Create event agenda and speaker schedule | Event Planner | 2024-05-13 | In Progress | Final review scheduled for 5/10.
Post-Event Activities
Budget Summary (USD)
Category | Budgeted Amount | Actual Spend | Remaining
Projected Costs
Venue Rental | $2,500.00 | $2,350.00 | $150.00
Catering & Refreshments | $4,200.00 | $3,987.56 | $212.44
Audiovisual Equipment | $1,800.00 | $1,573.25 | $226.75
Marketing & Promotion | $800.00 | $645.33 | $154.67
Total Budget: | $9,300.00 | $8,556.14 | $743.86