## Worksheet
Task ID | Task Description | Assigned To | Due Date | Status | Priority | Budget (USD)
EVT-001 | Finalize Event Concept & Theme | Jane Doe | 2023-10-15 | In Progress | High | $2,500
EVT-002 | Secure Venue & Contract Signatures | Mark Taylor | 2023-11-05 | Pending | High | $15,000
EVT-003 | Develop Marketing & Promotion Strategy | Sarah Wilson | 2023-11-10 | In Progress | Medium | $5,800
EVT-004 | Confirm Catering & Menu Selection | Tom Bradley | 2023-11-20 | Pending | Medium | $8,900
EVT-005 | Coordinate Entertainment & Speakers | Lisa Chen | 2023-11-15 | Pending | High | $6,400
EVT-006 | Send Invitations & Track RSVPs | Emily Parker | 2023-12-01 | Pending | Medium | $1,500
EVT-007 | Finalize Event Timeline & Schedule | James Reed | 2023-12-10 | Pending | High | $3,200
EVT-008 | Conduct Full Event Rehearsal | Grace Lewis | 2023-12-15 | Pending | High | $4,000
EVT-009 | Execute Event Day Operations | All Team Members | 2023-12-18 | Pending | High | $7,500
EVT-010 | Post-Event Survey & Debrief Session | David Kim | 2023-12-25 | Pending | Low | $1,000
Total Budget:$66,700
Tasks Completed:0 / 10
Upcoming Deadline:December 18, 2023 (Event Day)